## DEVELOPMENT LOG
DEVELOPMENT LOG
PROJECT NAME | COMPUTERIZED ADAPTIVE TEST |  | PROJECT START DATE | 1 | 15/06/2020
15/06/2020
PROJECT MANAGER | Remston Dsa |  | PROJECT END DATE | 31/07/2020 | 31/07/2020
PLEASPLEASE REMOVE THE CONTENTS IN THE WHITE SPACE ON THE TABLE BEFORE START WORKING ON THE TABLE. THE DATA PROVIDED IS ONLY FOR REFERENCE PURPOSEE REMOVE THE CONTENTS IN THE WHITE SPACE ON THE TABLE BEFORE START WORKING ON THE TABLE. THE DATA PROVIDED IS ONLY FOR REFERENCE PURPOSE
SL NO | FEATURE NAME | VERSION CREATION DATE | VERSION LINK | VERSION CHANGE DESCRIPTION | DEVELOPMENT STATUS | REVIEW STATUS
1 | rasch model | 15/06/2020 |  | In the new version, a notification icon has been added to the navigation bar. | COMPLETED | REVIEWED
2 | weight | 22/06/2020 |  |  | COMPLETED | REVIEWED
3 | Plots | 29/06/2020 |  |  | COMPLETED | REVIEWED
4 | Model Fit | 2020-06-07 |  |  | COMPLETED | REVIEWED
5 | MAP and EAP | 13/07/2020 |  |  | COMPLETED | REVIEWED
6 | Training | 21/07/2020 |  |  | COMPLETED | REVIEWED
7 | Testing | 27/07/2020 |  |  | COMPLETED | REVIEWED