## Sheet1
PROJECT PLAN
DOCUMENT VERSION: 1.0
PROJECT NAME | Computerized Adaptive Test
PROJECT MANAGER | Remston Dsa
PROJECT DELIVERABLE | Cloud Counselage
PROJECT SCOPE
PROJECT START DATE | 15/06/2020
PROJECT END DATE | 31/07/2020
OVERALL PROGRESS | Completed
SL NO | TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION IN DAYS | STATUS
1 | Initiation
1.1 | Identify business problem |  | 15/06/2020 | 16/06/2020 | 1 | COMPLETED
1.2 | Check for Reference papers and Research papers |  | 16/06/2020 | 17/06/2020 | 1 | COMPLETED
1.3 | Create a project charter |  | 17/06/2020 | 20/06/2020 | 3 | COMPLETED
1.4 | Requirement gathering |  | 20/06/2020 | 22/06/2020 | 2 | COMPLETED
2 | Planning
2.1 | Collecting resources |  | 22/06/2020 | 23/06/2020 | 1 | COMPLETED
2.2 | Project Character |  | 23/06/2020 | 25/06/2020 | 2 | COMPLETED
2.3 | Project Plan |  | 25/06/2020 | 27/06/2020 | 2 | COMPLETED
2.4 | SRS Documentation |  | 27/06/2020 | 29/06/2020 | 2 | COMPLETED
3 | Execution
3.1 | Finalize design |  | 29/06/2020 | 30/06/2020 | 1 | COMPLETED
3.2 | Build |  | 2020-01-07 | 21/07/2020 | 21 | COMPLETED
3.2.1 | R Coding |  | 2020-01-07 | 2020-10-07 | 10 | COMPLETED
3.2.2 | Rasch Model implementation |  | 2020-10-07 | 14/07/2020 | 4 | COMPLETED
3.2.3 | IRT implementation |  | 14/07/2020 | 18/07/2020 | 4 | COMPLETED
3.2.4 | Probabilistic Approach |  | 18/07/2020 | 21/07/2020 | 3 | COMPLETED
3.3 | Testing |  | 21/07/2020 | 27/07/2020 | 7 | COMPLETED
3.3.1 | Manual testing |  | 21/07/2020 | 25/07/2020 | 5 | COMPLETED
3.3.2 | Automation testing |  | 25/07/2020 | 27/07/2020 | 2 | COMPLETED
4 | Closure |  | 27/07/2020 | 31/07/2020 | 4 | COMPLETED