## RAID LOG
RAID Log
Project title: | Computerized Adaptive Test |  | Project Id: |  | Project Manager: | Remston Dsa
DOCUMENT VERSION: |  |  | Last Updated date: | 28/07/2020 | Project Team Lead: | Cloud counselage
Select … |  |  |  |  | Select … | Risk Priority Number | Open/Closed
RAID Category | Description | Impact | Mitigation | Owner | Priority | RPN (for risks) | Status
Risk | Mutilation of Training Dataset | Impact on the predictions and weights | Large dataset is used | Project Manager | Critical |  | Open
Risk | high computational cost | impact on performance and speed | Machine Learning Algorithms are implemented like knn,Decision trees | Project Manager | High |  | Closed
Assumption | The responses are in consecutive order | Impact on predictions | Predefined dataset is used for predictions | Project Manager | High |  | Open
Assumption | Weights of questions are accurately measured | Impact on Accuracy in measurement of Test takers caliber | Trained for Large and predefined dataset | Project Manager | Moderate |  | Closed
Issue | The test takers cannot skip the questions | Impact on test takers performance and improper weightage of questions |  | Project Manager | High |  | Open
Issue | The dimensions of testing and training must match | Impact on Knn Algorithm as dimensions of test and train mismatch | Implementation of decision tress for logistic regression | Project Manager | Low |  | Open
Dependency | Algorithm | Impact on calculation of weights for each questions | Implementation of decision tress,knn for logistic regression | Project Manager | Moderate |  | Closed